## Sheet1
work area | work item | description | approach | current status | next step | comment
Finance | Official account | We need an official bank account through which all the income and expenses are handled, i.e., registration fee or catering money. | Prof. Lee kindly mentioned that we may use the bank account of Taiwanese Physical Society. The society also can issue a receipt so that people can get reimbursed. | Prof. Lee contacts Taiwanese Physical Society to figure out whether it will provide the service. | We will decide on the official account.
| Budget | Shall we plan a budget, i.e., how much income we can expect and how much we'll spend.
| Income | Shall we figure our our income? Registration fee and sponsors? We need a way for on-line payment for registration with a credit card. We also decide how much we will charge for 1) on-site participation and 2) on-line participation. We shall be able to issue a receipt. | 1. We may charge 300 Euro for on-line registration. 2. Taiwanese Physics Society may handle on-line payment for registration for our stead. It may receive payment and issue a receipt. 3. It's not clear whether we'll allow on-site participation withour a priori registration. | Prof. Lee contacts Taiwanese Physics Society to figure out whether it will provide the service. | We'll decide on 1. on-line registration fee and 2. whether we'll allow on-site participation and how much we will charge.
| Expense | We need a way to pay the expense. Shall we collect receipts and submit them to some entities? | 1. Taiwanese Physics Society may handle the payment of our expenses, e.g., catering. | Prof. Lee contacts Taiwanese Physical Society to figure out whether it will provide the service. | We'll decide on payment method for our expenses.
Registration | Web page | We need a webpage to provide 1) basic info, 2) program, 3) registration method with payment. | We have a web page eacn.eu with registration https://indico.physik.uni-muenchen.de/event/208/ | We have no method for on-line registraion payment. Taiwanese Physics Society may remedy this deficiency.
| On-line Registration with payment | We need a webpage to receive on-line registration with payment. - Payment shall be transferred to the official bank account. - The list of participants shall be managed by somebody. | We may coopearte with Taiwanese Physical Society to handle on-line registration payment. We may figure out a way to automatically generate the list of participants. - Janis, Simon, Christian have access to the list |  | We provide the way for 1. on-line registraion payment 2. participation list generation.
| On-site Registration | We may allow a way for a person to register on-site without online registration. |  |  | We'll decide on whether we'll allow on-site participation and how much we will charge.
Program | Speakers | We need to invite speakers along with the topic. | Peter van Loock (Johannes Gutenberg Universität Mainz, Germany) Norbert Hanik (Technische Universität München, Germany) Marc Geitz (Deutsche Telekom T-Labs, Germany) Ricardo Barrios (Airbus Defense and Space, Germany) Shahram Dehdashti (Technische Universität München, Germany)
| Agenda | We need to develop a MON-WED program.
| Presentation material | We may post a presentation material along with a video online.
| Poster session & other competition | Stefano has in mind poster session and competition at THU and FRI.
Venue | Meeting room | We need a room with meeting facility - WiFi - Projector - Mike & Speaker | 浦大邦紀念講堂 Dr. Poe Lecture Hall in the National Taiwan University (NTU) campus. | There will be ICSSUR 2023 the next week at the same place. We can reasonably expect there will be meeting facilities.
| On-line streaming | We may provide on-line streaming for on-line participants.
Workshop logistics | On-site registration (with name tag) | We need a person or two onsite to receive participants and 1. check the attendee list, 2. issue a name tag 3. distribute souvenir,e.g., T-shirt.
| Souvenir & name tag | We need to prepare 1) souvernir and 2) name tag.
| Lunch | We may provide lunch to participants. | Catering service?
| Snack | We may provide snack, i.e., 1) coffee and 2) cookies.